## Drainage & Flood Alleviation
Flood Alleviation Programme
Flood Alleviation Schemes which will mitigate flood risk associated with the surface water network of streams, rivers and culverts
Status Report - July 2017
Project Name | Description | Status
Ardglas Screen Upgrade | Screen upgrade in environs of Ardglas, Dundrum | Modelling completed. Commission awarded for design of works. Work is progressing on design
Cabinteely Park Flood Storage Feasibility Study | Feasibility Study to investigate Flood Storage Measures in Cabinteely Park | Hydraulic modelling work underway. Feasibility report completed. Liaison ongoing with DLR Parks Section
Fernhill Park Flood Storage Feasibility Study | Feasibility Study to investigate if new pond in Fernhill Park can accommodate storm waters | Feasibility study is complete. Liaison ongoing with DLR Parks Section
Glenavon Park Flood Storage Online Attenuation | Construction of on-line flood storage pond and constructed wetlands | Feasibility Study Completed. The study recommended further detailed flow measurement surveys and analysis - now completed. Estimated completion Quarter 3 2017
Installation of Screen Monitoring Cameras | Installation of screen monitoring cameras which identify screen blockages | Installation of cameras is ongoing. Screen monitoring cameras were erected at sites in Loreto Park, Seafield, Blackrock and Ulster Terrace
Johnstown Road Environs | Design of upgraded channel layout and stream bank and local drainage improvements | Culvert removal works are complete. Stream re-alignment work is completed. New screen and bank works are nearing completion
Kilbogget Park Screen Upgrade | Upgrade of the culvert screen and creation of online flood storage area in the environs of the constructed wetlands | Design work has commenced. Ground investigation contract is complete. Part 8 documentation preparation underway
Marlay Park Enhanced Flood Storage | Increasing capacity of the Storage Pond in Marlay Park | The final consultants report has been received. An Ecological Impact Report is now complete. Preliminary Design to start in Quarter 3
Old Dublin Road Culvert Watermain Removal | Diversion of utilities from the culvert on the Old Dublin Road at St. Brendans College to alleviate flooding at this location | Ground Investigation and Detailed Design works completed. An advance contract (new valves etc) has been completed. Tenders received for the main civil works. Evaluation underway
Sandyford Park Flood Storage Feasibility Study | Feasibility Study to investigate Flood Storage measures in Sandyford Park | Feasibility Study is underway. Report due in Quarter 4 2017
Watsons Estate Pipeline Rehabilitation | Rehabilitation of severely fractured 300m diameter Surface Water Sewer | Phase 1 works completed in February 2017

## Coastal Protection
Status Report - July 2017
Project Name | Description | Status
Corbawn Coastal Protection Works | Proposed works consist of the construction of 240 metres of cliff stabilisation measures at the pedestrian access to the seafront at the end of Corbawn Lane; underpinning of the existing concrete step structure; protection of the base of the cliff using rock armour and concrete wing walls to the existing concrete step structure​ | Liaison completed with landowners. Detailed design completed. 3D survey of cliffs completed. Tendering due to commence in Quarter 3 2017