## Drainage & Flood Alleviation
Flood Alleviation Programme
Flood Alleviation Schemes which will mitigate flood risk associated with the surface water network of streams, rivers and culverts
Status Report
Project Name | Description | Status
Ardglas Screen Upgrade | Screen upgrade and associated flood storage measures in environs of Ardglas, Dundrum | Detailed design completed
Cabinteely Park Flood Storage Feasibility Study | Feasibility Study to investigate Flood Storage Measures in Cabinteely Park | Report due for completion in Quarter 2 2017. Hydraulic modelling work is now complete
Fernhill Park Flood Storage Feasibility Study | Feasibility Study to investigate if new pond in Fernhill Park can accommodate storm waters | Feasibility Study is underway. Report is due in Quarter 3 2017. Hydraulic modelling work commenced in March 2017
Glenavon Park Flood Storage Online Attenuation | Construction of on-line flood storage pond and constructed wetlands | Feasibility Study Completed. The study recommended further detailed flow measurement surveys and analysis. Flow Surveys are underway. Estimated completion Quarter 3 2017
Installation of Screen Monitoring Cameras | Installation of screen monitoring cameras which identify screen blockages | Installation of cameras is ongoing. Screen monitoring cameras were erected at sites in Loreto Park, Seafield, Blackrock
Johnstown Road Environs | Design of upgraded channel layout and stream bank and local drainage improvements | Culvert removal works are completed. Stream realignment works are underway and are due for completion in Quarter 2 2017. New screen and bank works are due to commence and be completed in Quarter 3 2017
Kilbogget Park Online Attenuation | Upgrade of the culvert screen and creation of online flood storage area in the environs of the constructed wetlands | Preliminary Design Works have commenced. Tenders have been received for a ground investigation contract
Marlay Park Enhanced Flood Storage | Increasing capacity of the Storage Pond in Marlay Park | The final consultants report has been received. An Ecological Impact Report is planned to commence in Quarter 2 2017
Old Dublin Road Culvert Watermain Removal | Diversion of utilities from the culvert on the Old Dublin Road at St. Brendans College to alleviate flooding at this location | Advance works (new valves etc) will take place in April 2017. Main civil works will be tendered in early Quarter 2 2017. Works due for completion in Quarter 3 2017
Sandyford Park Flood Storage Feasibility Study | Feasibility Study to investigate Flood Storage measures in Sandyford Park | Feasibility Study is underway
Watsons Estate Pipeline Rehabilitation | Rehabilitation of severely fractured 300m diameter Surface Water Sewer | Phase 1 works completed in February 2017

## Coastal Protection
Status Report
Project Name | Description | Status
Corbawn Coastal Protection Works | Proposed works consist of the construction of 240 metres of cliff stabilisation measures at the pedestrian access to the seafront at the end of Corbawn Lane; underpinning of the existing concrete step structure; protection of the base of the cliff using rock armour and concrete wing walls to the existing concrete step structure​ | Detailed design is underway. A 3D survey of cliffs will be tendered early in Quarter 2 2017