## Flood Alleviation
Flood Alleviation Programme
Flood Alleviation Schemes mitigating flood risk associated with the surface water network of streams, rivers and culverts
Status Report - April 2019
Project Name | Description | April 2019 Status
Cabinteely Park Flood Storage Feasibility Study | Feasibility Study to investigate Flood Storage Measures in Cabinteely Park | Feasibility report complete. Concept/preliminary design complete. Project subsumed into OPW's ECFRAM projects.
Fernhill Park Flood Storage Feasibility Study | Feasibility Study to investigate if new pond in Fernhill Park can accommodate storm waters | Feasibility report complete. Parks are progressing preliminary design.
Glenavon Park Flood Storage Online Attenuation | Construction of on-line flood storage pond and constructed wetlands | The Feasibility Study has been completed. Project subsumed into the OPW's ECFRAM Projects.
Installation of Screen Monitoring Cameras | Installation of screen monitoring cameras which identify screen blockages and assist with monitoring river levels | Installation of cameras is ongoing.
Kilbogget Park Screen Upgrade | Upgrade of the culvert screen and creation of online flood storage area in the environs of the constructed wetlands | Part 8 approval granted at Council meeting in September 2018. Detailed design scheduled to commence May 2019 as an advance project for OPW's ECFRAM Scheme.
Dundrum Slang; M50 Jn 13 Environs Flood Storage | Assess feasibility of enhancing flood storage | Topographic survey complete. Ground investigation complete. CCTV survey complete. Modelling work underway.
Dundrum Slang Integrated Catchment Model | Develop an integrated river model to assess flood risk management options | Tender evaluation complete and project has been awarded. Flow/rainfall survey has commenced. Topographical survey completed. Modelling work underway.