## Drainage & Flood Alleviation
Flood Alleviation Programme
Flood Alleviation Schemes which will mitigate flood risk associated with the surface water network of streams, rivers and culverts
Status Report
Project Name | Description | Status
Ardglas Screen Upgrade | Screen upgrade and associated flood storage measures in environs of Ardglas, Dundrum | Detailed design completed
Cabinteely Park Flood Storage Feasibility Study | Feasibility Study to investigate Flood Storage Measures in Cabinteely Park | Report due for completion in Quarter 2 2017. Hydraulic modelling work is now complete
Fernhill Park Flood Storage Feasibility Study | Feasibility Study to investigate if new pond in Fernhill Park can accommodate storm waters | Feasibility Study is underway. Report is due in Quarter 3 2017. Hydraulic modelling work commenced in March 2017
Glenavon Park Flood Storage Online Attenuation | Construction of on-line flood storage pond and constructed wetlands | Feasibility Study Completed. The study recommended further detailed flow measurement surveys and analysis. Flow Surveys are underway. Estimated completion Quarter 3 2017
Installation of Screen Monitoring Cameras | Installation of screen monitoring cameras which identify screen blockages | Installation of cameras is ongoing. Screen monitoring cameras were erected at sites in Loreto Park, Seafield, Blackrock
Johnstown Road Environs | Design of upgraded channel layout and stream bank and local drainage improvements | Culvert removal works are completed. Stream realignment works are underway and are due for completion in Quarter 2 2017. New screen and bank works are due to commence and be completed in Quarter 3 2017
Kilbogget Park Online Attenuation | Upgrade of the culvert screen and creation of online flood storage area in the environs of the constructed wetlands | Preliminary Design Works have commenced. Tenders have been received for a ground investigation contract
Marlay Park Enhanced Flood Storage | Increasing capacity of the Storage Pond in Marlay Park | The final consultants report has been received. An Ecological Impact Report is planned to commence in Quarter 2 2017
Old Dublin Road Culvert Watermain Removal | Diversion of utilities from the culvert on the Old Dublin Road at St. Brendans College to alleviate flooding at this location | Advance works (new valves etc) will take place in April 2017. Main civil works will be tendered in early Quarter 2 2017. Works due for completion in Quarter 3 2017
Sandyford Park Flood Storage Feasibility Study | Feasibility Study to investigate Flood Storage measures in Sandyford Park | Feasibility Study is underway
Watsons Estate Pipeline Rehabilitation | Rehabilitation of severely fractured 300m diameter Surface Water Sewer | Phase 1 works completed in February 2017

## Corbawn Coastal Prot
Updated 16/05/17
Status
Project Name | Description | Status
Corbawn Coastal Protection Works | Proposed works consist of the construction of 240 metres of cliff stabilisation measures at the pedestrian access to the seafront at the end of Corbawn Lane; underpinning of the existing concrete step structure; protection of the base of the cliff using rock armour and concrete wing walls to the existing concrete step structure​ | Detailed design is underway. A 3D survey of cliffs will be tendered early in Quarter 2 2017
Note: Only the information under Status, should be updated for Corbawn Coastal Protection Works on the Website

## Project List
List of Projects
Ardglas Screen Upgrade
Cabinteely Park Flood Storage Feasibility Study
Fernhill Park Flood Storage Feasibility Study
Kilbogget Park Online Attenuation
Installation of Screen Monitoring Cameras
Johnstown Road Environs
Kilbogget Park Online Attenuation
Marlay Park Enhanced Flood Storage
Old Dublin Road Culvert Watermain Removal
Sandyford Park Flood Storage Feasibility Study
Watsons Estate Pipeline Rehabilitation
Corbawn Coastal Protection Works