## Flood Alleviation
Flood Alleviation Programme
Flood Alleviation Schemes mitigating flood risk associated with the surface water network of streams, rivers and culverts
Status Report - February 2019
Project Name | Description | Jan 2019 Status
Cabinteely Park Flood Storage Feasibility Study | Feasibility Study to investigate Flood Storage Measures in Cabinteely Park | Feasibility report complete. Concept/preliminary design complete. Project on hold pending direction from the OPW.
Fernhill Park Flood Storage Feasibility Study | Feasibility Study to investigate if new pond in Fernhill Park can accommodate storm waters | Hydraulic modelling work commenced in March 2017. Feasibility report complete. Parks are progressing preliminary design.
Glenavon Park Flood Storage Online Attenuation | Construction of on-line flood storage pond and constructed wetlands | The Feasibility Study has been completed and recommended further detailed flow measurement surveys and analysis. This additional survey/analysis work is now completed. Final report received. Detailed review and design scheduled to commence Q2 2019.
Installation of Screen Monitoring Cameras | Installation of screen monitoring cameras which identify screen blockages and assist with monitoring river levels | Installation of cameras is ongoing. Screen monitoring cameras were erected at sites in Loreto Park, Seafield, Blackrock, Ulster Terrace, Kilbogget Park, Woodbrook, Monkstown, Dargle View.
Kilbogget Park Screen Upgrade | Upgrade of the culvert screen and creation of online flood storage area in the environs of the constructed wetlands | Part 8 approval granted at Council meeting in September 2018. Detailed review and design scheduled to commence Q2 2019.
Dundrum Slang; M50 Jn 13 Environs Flood Storage | Assess feasibiltiy of enhancing flood storage | Preliminary design work has commenced. Topographic survey complete. Ground investigation complete. CCTV survey complete.
Dundrum Slang Integrated catchment Model | Develop an integrated river model to assess flood risk management options | Tender evaluation complete and project has been awarded. Flow/rainfall survey has commenced. Topographical survey tendered.