**DLR procurement greater than €10m**

|  |
| --- |
| **Project Details** |
| Year: | 2023 |
| Parent Department: | Housing Department |
| Name of Contracting Body: | Dun Laoghaire Rathdown County Council |
| Name of Project/Description: | Housing and New Library, St. Laurence’s Park, Stillorgan |
| **Procurement Details** |
| Advertisement Date: | 8th September 2021 |
| Tender Advertised in: | eTenders and OJEU |
| Awarded to: | Clancy Project Management Ltd |
| EU Contract Award Notice Date: | 13th September 2023 |
| Contract Price: | €32,894,046 (Ex. VAT @ 13.5%) |
| **Progress** |
| Start Date: | 9th October 2023 |
| Expected Date of Completion per Contract: | October 2025 |
| Spend in Year under Review: | €1,302,512 inc VAT |
| Cumulative Spend to End of Year: | €1,302,512 inc VAT |
| Projected Final Cost: | €33,175,742.74 (Ex. VAT @ 13.5%) |
| Value of Contract Variations: | €281,696.74 (Ex. VAT @ 13.5%) |
| Date of Completion: | Estimated January 2026 |
| **Outputs** |
| Expected Output on Completion(E.G. XX kms of Road, No of units etc) | 88 dwellings and new 2-storey Library |
| Output Achieved to date(E.G. X kms of Roads, No of Units etc) |  |