## Sheet1
Flood Alleviation Programme
Flood Alleviation Schemes mitigating flood risk associated with the surface water network of streams, rivers and culverts
Status Report - October 2024
Project Name | Description | October 2024 Status
Deansgrange ECFRAM Flood Alleviation Scheme | Flood Risk Management works on the Deansgrange Stream. | The project received Part 8 Planning approval at the December 2024 Council meeting. Design work and advance projects (invasives removal etc) are now progressing on the different elements of the project.
Carrickmines/Shanganagh Flood Alleviation Scheme | Flood Risk Management works on the Carrickmines/Shanganagh/Loughlinstown Rivers. | The preferred option was presented to stakeholders at a public engagement event in December 2023. The Options Report is finalised and an Environment Impact Assessment Report is subsatnatially completed. It is proposed to submit a planning application to An Bord Pleanala in Q4 2024.